## Sheet1
task | time estimation (in hours)
problem analisis | 0.5
db schema planing and implementation | 1
sesign selection and basic preparation | 0.5
fontend static forom | 1
from validation and saving | 0.5
backend panel with admin login with captcha validation | 1.5
backend listing | 0.5
view with google map | 2
testing an resurved hours | 2
total | 9.5